## Compliance Matrix
ID | Section | Requirement | Source / Page | Category | Obligation Level | Classification Rationale | Proposed Owner | Evidence / Response Needed | Readiness Status | Addendum Impact | Notes / Risk
S01 | I. Comprehensive Solution | Provide one enterprise CRM with a single data architecture and user interface. | Base RFP p.11 | Platform | Mandatory | The Scope says these requirements are mandatory. | Technical Team | Explain the overall platform and architecture. | Vendor input needed | Clarified by Addendum 2 | A shared-data-model solution may be acceptable if it still works as one platform.
S02 | I. Comprehensive Solution | Do not rely on several loosely connected third-party systems for the main CRM functions. | Base RFP p.11 | Platform | Mandatory | Troy says the solution should not be a collection of separate systems. | Technical Team | Explain how the main CRM functions work together. | Vendor input needed | Clarified by Addendum 2 | The main aim is one unified working environment.
S03 | I. Comprehensive Solution | If third-party components are used, they must work as part of the main platform with a unified data model and user experience. | Base RFP pp.11–12 | Platform / Integration | Conditional mandatory | Only applies if third-party components are part of the proposed solution. | Technical Team | Explain how any third-party components connect and work with the CRM. | Vendor input needed | No major change
S04 | I. Comprehensive Solution | Identify any third-party components and explain data consistency, user experience, security and licensing. | Base RFP p.12 | Platform / Integration | Conditional mandatory | Required if third-party components are included. | Technical Team | List third-party components and explain how they are managed. | Vendor input needed | No major change
S05 | II. Technical, Platform & Security | Provide a secure, web-based, vendor-hosted cloud CRM. | Base RFP p.12 | Technical / Security | Mandatory | Listed as a required technical feature. | IT / Security | Describe hosting, cloud setup and security approach. | Vendor input needed | Clarified by Addendum 2 | Addendum also asks vendors to explain where data is hosted.
S06 | II. Technical, Platform & Security | Support major browsers including Chrome, Firefox, Safari and Edge. | Base RFP p.12 | Technical | Mandatory | Listed as a required technical feature. | Technical Team | Confirm browser support. | Vendor input needed | No major change
S07 | II. Technical, Platform & Security | Integrate with Ellucian Colleague and related Ellucian systems. | Base RFP p.12 | Integration | Mandatory | Integration with Colleague is directly required. | Integration Team | Explain the Colleague integration approach. | Vendor input needed | Clarified by Addendum 2 | Troy uses APIs/Ellucian Ethos and expects vendor-managed integration.
S08 | II. Technical, Platform & Security | Provide mobile-responsive functionality for users and staff. | Base RFP p.12 | Technical | Mandatory | Listed as a required technical feature. | Technical Team | Confirm mobile-responsive support. | Vendor input needed | No major change
S09 | II. Technical, Platform & Security | Allow restricted or limited-access portal views for internal and external users. | Base RFP p.12 | Security / Access | Mandatory | Listed as a required technical feature. | IT / Security | Explain how access and portal views can be controlled. | Vendor input needed | Clarified by Addendum 2 | Portal experiences may vary by user group.
S10 | II. Technical, Platform & Security | Provide pricing based mainly on workload or volume rather than only named/concurrent users. | Base RFP p.12; Addendum 2 p.26 | Commercial | Mandatory in base RFP, relaxed by Addendum 2 | The base RFP gives a pricing rule, but the addendum allows user-based pricing if it is explained. | Finance / Commercial | Provide pricing model and explain any user licence options. | Vendor input needed | Modified by Addendum 2 | User-based pricing may be accepted if the licence options are clearly explained.
S11 | III. Data Integration Architecture | Support bi-directional data exchange between the CRM, Ellucian Colleague and other required systems. | Base RFP p.12 | Integration | Mandatory | The RFP directly requires bi-directional integration. | Integration Team | Explain data flows and integration methods. | Vendor input needed | Clarified by Addendum 2 | Addendum gives examples of the data that may move between systems.
S12 | III. Data Integration Architecture | Use real-time or near-real-time API integration where possible. | Base RFP p.12 | Integration | Preferred | The RFP says this approach is strongly preferred. | Integration Team | Explain available real-time API capabilities. | Vendor input needed | Clarified by Addendum 2 | Troy again states a preference for real-time API integration.
S13 | III. Data Integration Architecture | If batch/SFTP is used, the vendor must host and manage it, monitor it, reconcile data and include the related costs. | Base RFP p.12 | Integration | Conditional mandatory | Only applies if batch or file-based exchange is used. | Integration Team | Explain file exchange, monitoring, error handling and costs. | Vendor input needed | Clarified by Addendum 2 | Troy confirms the vendor should host and monitor SFTP/file exchange.
S14 | III. Data Integration Architecture | Maintain all integration points during the contract, including changes caused by upgrades or version changes. | Base RFP p.12 | Integration | Mandatory | The vendor is given ongoing responsibility for integrations. | Integration Team | Explain ongoing integration support and maintenance. | Vendor input needed | Clarified by Addendum 2 | Addendum confirms the awarded vendor manages integration changes.
S15 | IV. Data Migration | Create and carry out a structured migration plan for Ellucian Recruit and any other agreed legacy sources. | Base RFP p.12 | Data Migration | Mandatory | The RFP directly requires a migration plan. | Data Team | Describe migration approach and source systems. | Vendor input needed | Clarified by Addendum 2 | Some migration from other tools may also be needed.
S16 | IV. Data Migration | Migrate prospect, application, status, communication, document, event and attribution data as required. | Base RFP p.13 | Data Migration | Mandatory with some scope still open | The data types are listed in the RFP, but some historical depth is still undecided. | Data Team | Confirm what data can be migrated and how much history can be included. | Vendor input needed | Clarified by Addendum 2 | Historical depth and some communication/document migration details are still being discussed.
S17 | IV. Data Migration | Include mapping, cleansing, validation, test migrations, cutover and rollback planning. | Base RFP p.13 | Data Migration | Mandatory | These activities are specifically required in the migration plan. | Data Team | Explain the migration steps and controls. | Vendor input needed | No major change
S18 | IV. Data Migration | Include migration services in the proposed cost unless Troy approves otherwise in writing. | Base RFP p.13 | Commercial / Data Migration | Mandatory | The RFP says migration should not be treated as an optional extra unless approved. | Finance / Data Team | Confirm migration pricing is included. | Vendor input needed | No major change
S19 | V. Identity & Account Lifecycle | Provide identity and account management for applicants, prospects and other external users. | Base RFP p.13 | Security / Access | Mandatory | The RFP directly requires identity and account lifecycle management. | IT / Security | Explain account creation, identity management and access controls. | Vendor input needed | Clarified by Addendum 2 | Troy says the vendor must provide and manage the identity solution.
S20 | V. Identity & Account Lifecycle | Support secure accounts, password controls, sessions, role-based access, FERPA controls, audit logs and optional MFA. | Base RFP p.13 | Security / Access | Mandatory with optional MFA feature | Most controls are required; MFA capability is listed as optional in the base RFP. | IT / Security | Describe access controls, audit logging and MFA options. | Vendor input needed | Clarified by Addendum 2 | MFA is described as preferred in the addendum.
S21 | VI. Prospect, Marketing & Recruitment | Track prospects through inquiry, application, decision, yield and enrolment stages. | Base RFP p.13 | Functional / Recruitment | Mandatory | This is a core CRM requirement in the Scope. | CRM / Recruitment Team | Explain lifecycle and pipeline tracking. | Vendor input needed | No major change
S22 | VI. Prospect, Marketing & Recruitment | Support marketing attribution, campaign dashboards, funnel tracking, ROI and cost-per-acquisition reporting. | Base RFP pp.13–14 | Marketing / Reporting | Mandatory | These reporting and attribution functions are listed in the Scope. | Marketing / Reporting Team | Explain campaign, funnel and ROI reporting. | Vendor input needed | Clarified by Addendum 2 | Troy identifies analytics and attribution as current pain points.
S23 | VI. Prospect, Marketing & Recruitment | Support segmentation, lookalike audiences, scoring and multiple lead/origin sources. | Base RFP p.14 | Marketing | Mandatory | These capabilities are directly listed in the Scope. | Marketing / CRM Team | Explain segmentation, scoring and attribution features. | Vendor input needed | Clarified by Addendum 2 | Troy already uses some lead scoring/segmentation approaches.
S24 | VII. Communication & Engagement | Support email and SMS, HTML/branded email, contact preferences and communication management. | Base RFP p.14 | Communications | Mandatory | Communication features are listed as required CRM functions. | CRM / Marketing Team | Explain email, SMS and communication tools. | Vendor input needed | Clarified by Addendum 2 | Email and campaign automation should be native; two-way SMS is welcome but not required.
S25 | VII. Communication & Engagement | Capture email conversations and keep an auditable communication history, separating recruiter activity from marketing activity. | Base RFP p.14 | Communications | Mandatory | The RFP requires complete and traceable communication records. | CRM / Marketing Team | Explain communication history and audit trail. | Vendor input needed | No major change
S26 | VII. Communication & Engagement | Use AI or advanced analytics to support communication personalisation. | Base RFP p.14 | AI / Analytics | Mandatory outcome | The RFP requires AI or advanced analytics, so AI itself is not the only possible method. | CRM / Analytics Team | Explain personalisation, AI or advanced analytics features. | Vendor input needed | Clarified by Addendum 2 | Troy asks for detailed AI capability information and may evaluate AI features.
S27 | VIII. Admissions, Applications & Forms | Support online applications, conditional logic, RFI/forms, secure payments and admissions workflows. | Base RFP p.14 | Admissions | Mandatory | These are directly listed application and admissions requirements. | Admissions / CRM Team | Explain application, forms, payment and workflow features. | Vendor input needed | Clarified by Addendum 2 | Troy confirms multiple application types, conditional logic and application fees.
S28 | VIII. Admissions, Applications & Forms | Support catalog year, different start terms and separation of applicants from opportunity/pipeline records. | Base RFP p.14 | Admissions | Mandatory | These are specifically listed in the Scope. | Admissions / CRM Team | Explain how these admissions records and terms are managed. | Vendor input needed | No major change
S29 | VIII. Admissions, Applications & Forms | Provide fraud-prevention options or explain how fraud prevention can be handled through another integrated tool. | Base RFP p.14; Addendum 2 p.4 | Admissions / Security | Optional / desirable after addendum | The base RFP listed fraud tools, but Addendum 2 says fraud prevention inside the CRM is not required. | Admissions / IT Team | Explain available fraud controls or integration options. | Vendor input needed | Modified by Addendum 2 | Do not treat built-in fraud prevention as a strict mandatory requirement.
S30 | IX. Events, Travel & Outreach | Provide event management and recruiter travel tracking. | Base RFP p.14 | Events / Outreach | Mandatory | Both modules are directly required in the Scope. | CRM / Recruitment Team | Explain event registration, attendance, communications and travel tracking. | Vendor input needed | Clarified by Addendum 2 | Troy mentions tours/events, surveys and mobile check-in.
S31 | X. Data, Analytics, Reporting & Integrations | Provide analytics, reporting, data visualisation and shareable reports. | Base RFP pp.14–15 | Reporting / Analytics | Mandatory | Reporting and analytics are required in the Scope. | Reporting Team | Explain dashboards, reports and sharing options. | Vendor input needed | Clarified by Addendum 2 | Vendor must provide and manage its own reporting environment.
S32 | X. Data, Analytics, Reporting & Integrations | Support third-party data imports and integrations through API, SFTP and web services. | Base RFP p.15 | Integration | Mandatory | These integration methods are directly listed. | Integration Team | Explain supported integration methods and tools. | Vendor input needed | Clarified by Addendum 2 | Troy will not provide a separate data warehouse/reporting environment for this project.
S33 | X. Data, Analytics, Reporting & Integrations | Provide real-time or near-real-time visibility of student status changes and key onboarding milestones. | Base RFP p.15 | Reporting / Integration | Mandatory | The RFP directly requires status and onboarding visibility. | Integration / Reporting Team | Explain how student status and onboarding data will be updated and shown. | Vendor input needed | Clarified by Addendum 2 | Troy welcomes real-time updates for areas such as financial aid, housing and transcripts.
S34 | X. Data, Analytics, Reporting & Integrations | Do not automatically merge or suppress possible duplicate records before Troy reviews them. | Base RFP p.15 | Data Governance | Mandatory | The RFP specifically prevents automatic duplicate handling before review. | Data Team | Explain duplicate detection and review controls. | Vendor input needed | Clarified by Addendum 2 | Troy already has duplicate-management policies and procedures.
S35 | XI. SLA & Performance | State uptime, maintenance windows, response/resolution times, escalation, RTO and RPO. | Base RFP p.15 | SLA / Support | Mandatory | The proposal must provide these service-level details. | Support Team | Provide proposed SLA and recovery targets. | Vendor input needed | No major change
S36 | XI. SLA & Performance | Provide documented SLAs and explain disaster recovery/business continuity, including testing. | Base RFP p.15 | SLA / Security | Mandatory | The RFP directly requires SLAs and disaster-recovery evidence. | Support / IT Security | Provide SLA, DR/BCP approach and testing evidence. | Vendor input needed | No major change
S37 | XII. Project Governance & Implementation | Provide an implementation plan with phases, timing, roles, testing, training and post-implementation support. | Base RFP p.15 | Implementation | Mandatory | A detailed implementation plan is directly required. | Project Manager | Provide implementation plan and training/support approach. | Vendor input needed | Clarified by Addendum 2 | No fixed go-live date is given; Troy wants a mix of expert-led and self-study training.
S38 | XII. Project Governance & Implementation | State assumptions about Troy resources and any dependencies that may affect the timeline. | Base RFP p.15 | Implementation | Mandatory | The RFP directly asks for assumptions and dependencies. | Project Manager | List vendor assumptions, Troy inputs and project dependencies. | Vendor input needed | Clarified by Addendum 2 | Troy expects EM, Marketing and IT involvement, mostly part-time.
S39 | XIII. Data Ownership, Security & Exit | Troy keeps ownership of its data and the vendor cannot use or disclose it outside the contract purpose. | Base RFP p.16 | Data Governance / Legal | Mandatory | The RFP clearly states Troy's data ownership and use restrictions. | Legal / IT Security | Explain data ownership, access and use controls. | Vendor input needed | Clarified by Addendum 2 | Addendum reinforces data governance and ownership expectations.
S40 | XIII. Data Ownership, Security & Exit | Do not use Troy data to train external AI/ML models without written permission. | Base RFP p.16 | AI / Data Governance | Mandatory | The RFP specifically restricts AI/ML training use. | IT Security / Legal | Explain AI data-use controls. | Vendor input needed | Clarified by Addendum 2 | The addendum gives more detail on AI governance and security expectations.
S41 | XIII. Data Ownership, Security & Exit | At contract end, export Troy data, provide supporting data documentation, securely delete remaining copies and support transition. | Base RFP p.16 | Data Governance / Exit | Mandatory | These exit actions are directly required. | Technical / Legal Team | Explain data export, deletion and transition process. | Vendor input needed | No major change
S42 | X. Data, Analytics, Reporting & Integrations | Provide and manage the reporting tool and reporting environment used for this project. | Addendum 2 p.25 | Reporting / Analytics | Mandatory | Troy says its existing Power BI/Tableau environment will not be available for this project. | Reporting Team | Describe the reporting platform/environment included in the solution. | Vendor input needed | New clarification | This was made clear in the Q&A.
S43 | VII / XIII. AI & Data Governance | Identify all AI features and explain the data sources, processing methods and safeguards used. | Addendum 2 pp.24, 34 | AI / Security | Mandatory | The addendum directly asks vendors to disclose this information. | IT Security / Technical Team | Provide AI feature and safeguard details. | Vendor input needed | New clarification | Keep AI claims evidence-based.
S44 | XIII. Data Ownership, Security & Exit | Explain where Troy data will be stored, processed and backed up, including any subcontractors or cloud providers. | Addendum 2 pp.24, 35 | Security / Data Governance | Mandatory | The addendum directly asks for data residency and hosting information. | IT Security | Provide data location, hosting and subprocessor details. | Vendor input needed | New clarification | US hosting should be prioritised unless Troy approves otherwise.
S45 | XIII. Data Ownership, Security & Exit | Confirm that the solution does not rely on technologies restricted under applicable federal guidance. | Addendum 2 pp.24, 35 | Security / Compliance | Mandatory | The addendum specifically requires this certification. | IT Security / Legal | Provide compliance confirmation. | Vendor input needed | New clarification | Relates to federal supply-chain restrictions.
Compliance Matrix

## Source Register
Source Register
Document | What I used it for | Main update / importance | Official source
Base RFP – Troy University RFP #26-004 CRM Software | Main source for scope, proposal format, evaluation and bid requirements. | This is the original RFP and the starting point for the analysis. | https://www.troy.edu/_assets/financial-affairs-and-online-education/departments/purchasing/_documents/26-004-crm-software-rfp-package.pdf
Addendum No. 1 | Checked for changes to key dates. | Changed the proposal deadline to 7 April 2026 at 2:00 PM CST. | https://www.troy.edu/_assets/financial-affairs-and-online-education/departments/purchasing/_documents/rfp-26-004-customer-relations-management-crm-addendum1.pdf
Addendum No. 2 – Q&A | Used to clarify requirements, submission details, pricing, integrations, migration and security. | Some requirements were clarified, modified or expanded. | https://www.troy.edu/_assets/financial-affairs-and-online-education/departments/purchasing/_documents/rfp-26-004-customer-relations-management-crm-addendum2.pdf

## Summary
Summary
Item | Details
Project | RFP Compliance & Response Readiness Case Study
RFP analysed | Troy University RFP #26-004 – CRM Software
Type of project | Independent portfolio / learning project
Main purpose | To understand a real RFP and organise the requirements, submission items, risks and response work in a structured way.
Documents reviewed | Base RFP, Addendum No. 1 and Addendum No. 2
Requirements recorded | 45
Main workbook sections | Compliance Matrix, Source Register, Summary, Submission Checklist, Risk & Clarification Log, Response Plan
Evaluation weighting | 15 points – company experience/references; 55 points – operation plan/ease of use/services; 30 points – fees
Main open areas | Go-live date, historical migration depth, and some decisions about which existing tools will be replaced or integrated.
How unknown information was handled | Vendor-specific information was marked as 'Vendor input needed' instead of being assumed.
Important note | This is not a real submitted proposal and no vendor capabilities, pricing or certifications were invented.

## Submission checklist
ID | Submission Item | Source/Page | Required? | When Needed | Likely Owner | Status | Notes
SUB-01 | Signed Troy University cover sheet | Base RFP p.22 | Yes | With proposal | Proposal Team | Identified | Must be signed by an authorised company representative.
SUB-02 | Complete bid response following the RFP structure | Base RFP pp.17–19, 22 | Yes | With proposal | Proposal Team | Identified | The proposal should follow the required sections and instructions.
SUB-03 | W-9 form | Base RFP p.22 | Yes | With proposal | Finance / Admin | Identified | Official bid checklist item.
SUB-04 | HECVAT Lite or accepted HECVAT Full v4 | Base RFP p.18; Addendum 2 p.10 | Yes | With proposal | IT / Security | Identified | Addendum 2 says Full v4 is accepted instead of Lite.
SUB-05 | Vendor Disclosure Form | Base RFP p.22; Addendum 2 p.10 | Preferred with bid | With proposal preferred; before contract finalisation required | Legal / Admin | Identified | Troy will accept it after award, but before the contract is finalised.
SUB-06 | E-Verify / Alabama Immigration documentation | Base RFP p.22; Addendum 2 p.10 | Preferred with bid | With proposal preferred; before contract finalisation required | HR / Legal | Identified | Troy will accept it after award, but before the contract is finalised.
SUB-07 | Performance Bond | Base RFP p.22; Addendum 2 p.9 | No at bid stage | After award, before contract finalisation | Finance / Legal | Post-award | Not required with the initial bid.
SUB-08 | Copies/acknowledgement of RFP addenda | Base RFP p.19 | Yes | With proposal | Proposal Team | Identified | Addenda should be acknowledged/included.
SUB-09 | Equal Opportunity Employment commitment | Base RFP p.10 | Yes | With proposal | HR / Legal | Identified | Required for consideration.
SUB-10 | ADA Section 508 compliance certification | Base RFP p.19 | Yes | With proposal | Compliance / Product Team | Identified | Vendor must certify compliance.
SUB-11 | Proposed service agreement | Base RFP p.5 | Yes | With proposal | Legal | Identified | Part of the proposed contract package.
SUB-12 | Two hard copies; one with original wet-ink signed documents | Addendum 2 p.10 | Yes | At submission | Proposal Team | Identified | Addendum 2 confirms the number of copies.
SUB-13 | USB digital copy | Addendum 2 p.10 | No | At submission | Proposal Team | Optional | Requested/appreciated, but not mandatory.
SUB-14 | Company profile and at least three higher-education references | Base RFP p.17 | Yes | With proposal | Proposal Team / Management | Identified | Section A.
SUB-15 | Detailed response to every Scope of Services point | Base RFP p.17; Addendum 2 p.11 | Yes | With proposal | Proposal Team + relevant teams | Identified | Each Scope point should be addressed in Section B.
SUB-16 | Pricing for all services | Base RFP p.18 | Yes | With proposal | Finance / Commercial | Identified | Section C.
SUB-17 | Hosting and disaster-recovery information | Base RFP p.18 | Yes | With proposal | IT / Security | Identified | Section D.
SUB-18 | Scalability approach and related costs | Base RFP p.18 | Yes | With proposal | Technical / Commercial | Identified | Section E.
SUB-19 | Implementation plan, timeline and training approach | Base RFP p.18 | Yes | With proposal | Project Manager | Identified | Section F.
SUB-20 | PCI compliance response | Base RFP p.18 | Yes | With proposal | IT / Compliance | Identified | Section G.
SUB-21 | Technical support and operations description | Base RFP p.18 | Yes | With proposal | Support Team | Identified | Section H.
SUB-22 | List any exceptions to the RFP | Base RFP p.18 | Yes, if applicable | With proposal | Proposal Team / Legal | Identified | Section I says exceptions should be referenced by subsection.
SUB-23 | Clearly mark any proprietary/confidential information | Base RFP p.19 | If applicable | With proposal | Proposal Team / Legal | Identified | Net cost information is not treated as confidential.
SUB-24 | Deliver proposal package to Troy University Purchasing by the revised deadline | Base RFP p.7; Addendum 1 | Yes | By 7 April 2026, 2:00 PM CST | Proposal Team | Identified | Physical delivery is required.
SUB-25 | Mark the outside of the proposal package with the RFP number and company details | Base RFP p.7 | Yes | At submission | Proposal Team | Identified | Helps make sure the package is correctly identified.

## Risk and clarification log
Risk & Clarification Log
ID | Issue / Uncertainty | Source/Page | Why It Matters | Impact | What Needs to Happen | Status
RISK-01 | No fixed go-live date | Addendum 2 pp.9, 25, 33 | The final implementation timeline cannot be confirmed yet. | Medium | Confirm the target go-live date before finalising the implementation plan. | Open
RISK-02 | It is not fully decided which current tools will be replaced and which will stay integrated | Addendum 2 pp.2, 26, 32 | This can change the solution design, integrations and pricing. | High | Confirm the final replace-vs-integrate scope. | Open
RISK-03 | Historical migration depth is still not fully decided | Addendum 2 pp.6, 29, 32 | More historical data can increase migration time and effort. | High | Confirm how many years/records need to be migrated. | Open
RISK-04 | Some existing data may have quality problems | Addendum 2 p.7 | Poor-quality data can make migration and validation harder. | Medium | Check data quality and cleansing needs before migration. | Open
RISK-05 | The length of the legacy-system parallel run is not clearly defined | Addendum 2 p.8 | A long overlap can affect transition planning and support. | Medium | Confirm the expected transition/parallel-run period. | Open
RISK-06 | Some AI governance details will be discussed during contract negotiations | Addendum 2 pp.11, 34–35 | The vendor may need to adjust AI features or controls later. | Medium | Review Troy's AI governance requirements before contract finalisation. | Open
RISK-07 | The base RFP lists fraud-prevention tools, but Addendum 2 says built-in fraud prevention is not required | Base RFP p.14; Addendum 2 p.4 | Using only the base RFP could lead to the wrong classification. | Medium | Use the addendum clarification and treat built-in fraud prevention as optional/desirable. | Resolved by Addendum 2
RISK-08 | Ongoing integration responsibility needed clarification | Base RFP p.12; Addendum 2 p.6 | It affects long-term support effort and cost. | Low | Record that the awarded vendor is responsible for maintaining the proposed integrations. | Resolved by Addendum 2
RISK-09 | Troy's budget for the project is still being discussed | Addendum 2 p.28 | There is no confirmed budget ceiling to guide pricing. | Medium | Prepare pricing based on scope and clearly state assumptions rather than guessing a budget. | Open

## Response plan
Response Plan
ID | Work Area | What Needs to Be Done | Priority | Likely Owner | Input Needed | Status
RP-01 | RFP Review | Review the base RFP and both addenda and confirm the latest requirements. | High | Proposal Team | Complete source documents | Completed
RP-02 | Compliance Check | Check each Scope requirement and note what vendor information would be needed to answer it. | High | Proposal Team + relevant teams | Compliance Matrix | Completed for case study
RP-03 | System Response | Prepare Section B answers for each Scope requirement in a real bid. | High | Technical / Business Teams | Vendor product and service information | Vendor input needed
RP-04 | Security & Hosting | Prepare HECVAT, hosting, security, data governance and disaster-recovery information. | High | IT / Security | Vendor security documents and hosting details | Vendor input needed
RP-05 | Implementation | Prepare the implementation approach, timeline, testing, training and dependencies. | High | Project Manager | Vendor implementation approach and Troy inputs | Vendor input needed
RP-06 | Company Experience | Prepare the company profile and higher-education references. | Medium | Proposal Team / Management | Vendor history and references | Vendor input needed
RP-07 | Pricing | Prepare complete pricing and make sure migration/integration costs are covered. | High | Finance / Commercial | Final technical scope and pricing model | Vendor input needed
RP-08 | Final Submission Check | Check forms, signatures, addenda, hard copies and all other submission items before delivery. | High | Proposal Team | Completed proposal and Submission Checklist | Not applicable to case study